## project WBS monitor
project: | Arduino WeatherStation |  |  | remark | WBS id is reference to chapter in functional design (FD)
calculator: |  |  |  | remark | for FD: chapter are not chronological
date: | 2017-03-10 |  |  | do not | change the WBS id number for a task
WBS id | predecessor | task | requirement level (MoSCoW) | developer | Risc | Expected Time | duration, hr (do) | evaluation (check) | action (act)
5 |  | Alle functie's werkend gekregen op één Arduino | MUST | William | Onvoldoende | 1
6 |  | Alle functie's werkend gekregen op één Arduino | MUST | Sven |  | 1
7 |  | Alle functie's werkend gekregen op één Arduino | MUST | Damien |  | 1
8 |  | Alle functie's werkend gekregen op één Arduino | MUST | Anthony |  | 1
9 |  | Temperatuursensor | MUST | Damien | Dat het op ene computer wel werkt en bij de ander niet. | 3
10 |  | Temperatuursensor | MUST | Sven |  | 3
13 |  | Vochtigheidsensor | MUST | Damien |  | 3
14 |  | Vochtigheidsensor | MUST | Sven |  | 3
17 |  | Windrichtin sensor | MUST | William |  | 3
18 |  | Windrichtingsensor | MUST | Sven |  | 3
|  | Luchtdruksensor | MUST | William |  | 3
|  | Luchtdruksensor | MUST | Sven |  | 3
|  | Compass in graden | MUST | William |  | 3
|  | Compass in graden | MUST | Sven |  | 3
|  | Drukknop switcht tussen sensoren | MUST | Anthony |  | 2
|  | LCD-Scherm | MUST | Anthony |  | 4
|  | Aparte onderdelen testen | MUST | Damien | Niet weten of de sensoren het doen. | 1.5 | 0.5 | check | Check
|  | WBS maken | MUST | Damien |  | 0.5 | 0.125 | check
|  | WBS maken | MUST | Sven |  | 0.5 | 0.125
|  | WBS maken | MUST | Anthony |  | 0.5 | 0.125
|  | WBS maken | MUST | William |  | 0.5 | 0.125 |  | Check
|  | Functioneel ontwerp | MUST | Sven | Onvoldoende | 1
|  | Project Plan | MUST | William | Onvoldoende | 3
|  | Debuggen | MUST | William | Er wordt niet gedebugd | 1
|  | Eindtest | COULD | Anthony | Er gaat iets kapot
|  | total |  |  |  | 48.5 | 1

## MoSCoW
M | MUST | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
S | SHOULD | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
C | COULD | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
W | WON'T | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).

## version
datum | door | versieomschrijving
2015-10-09 | kadi | originele basisversie aangepast aan ideeën van Six Sigma